APPROVED 30TH MAY 2006

CHAPTER I

- INTRODUCTION

This document serves as the 2006/ 07 Integrated Development Plan (IDP) for Mutale Local Municipality. In terms of Section 34 of the Local Government: Municipal Systems Act, 2000 (Act no. 33 of 2000) the IDP must be annually reviewed. The IDP 2006/ 07 was informed in the main by the following factors:

  - The comments made by the MEC for the Department of Local Government and Housing

  - Public inputs

  - Project consolidate Action Plan

  - MEC’s comments

The MEC’s comments are mainly based on the provisions of Section 26 of the Local Government: Municipal Systems Act, 2000 (Act no. 33 of 2000). The comments that have to be addressed are the following:

- Omission of Executive Summary

- Undefined projects and monetary value thereof

- List of needs instead of Priorities

- Inadequate Spatial Development Framework

- Non-adherence to time-frames

- Strategies not clearly related

- No indication of projected revenue

- Unclear Financial Plan

- Omission of some Sector Plans.

  - Public inputs

The Municipality collated public inputs mainly through ward-based community participation workshops, IDP Representative Forum. These inputs were consolidated and considered during the preparation of this Plan.

  - Project Consolidate Action Plan

Project Consolidate was introduced in late 2004 by the Ministry of Provincial and Local Government with the aim of assisting pre-identified municipalities to improve service delivery within their area of jurisdiction. In line with this, the Provincial Department of Local Government and Housing conducted a detailed capacity assessment on all Project Consolidate municipalities in the Province. It is against this background the Mutale Local Municipality developed its Project Consolidate Action Plan. The Action Plan was considered and integrated this document.

CHAPTER 2

- IDP REVIEW PROCESS PLAN

- INTRODUCTION

In accordance with the provisions of the Local Government: Municipal Systems Act, 2000 (Act No. 32 of 2000) & Local Government: Municipal Finance Management Act, 2003 (Act No. 56 of 2003) Mutale Municipality prepared this IDP Review and Budget 2006/ 07 Process Plan.  In the main this document addresses the following:

  - Programme for different planning steps

  - Procedures for consultation & participation of stakeholders

  - Identification & observation of binding plans & planning requirements

  - Institutional arrangements & participants’ roles & responsibilities

  - Budget allocation for the planning process

- INSTITUTIONAL ARRANGEMENTS & PARTICIPANTS’ ROLES & RESPONSIBILITIES

As the IDP/ Budget process is supposedly consultative and participatory in nature, roles and responsibilities of participants must be identified and clearly clarified. The roles and responsibility of participants are outlined as follows.

2.1. COUNCIL

- Adoption of the IDP Review/ Budget Process Plan

- Ensure the adherence of the planning process to timeframes

- Ensure the participation of all stakeholders in the review process

- Ensure that the plan is strategic & implementation orientated

- Adoption of the reviewed IDP & Budget

2.2 EXECUTIVE COMMITTEE

- Manage the compilation of the IDP Review/ Budget process

- Assign the responsibility in this regard to the Municipal Manager

- Table the IDP Review/ Budget Process Plan to the Council

- Table the reviewed IDP/ Budget to the Council

2.3. IDP MANAGER

- Prepare in consultation with the Chief Financial Officer a programme for IDP Review/ Budget

- Responsible for the overall management, coordination & monitoring of the planning process

- Ensure that all participants are appropriately involved in the planning process

- Ensure that the review process complies to set timeframes and budget

- Ensure that alignment procedures and mechanisms are adhered to

- Ensure that the planning process is strategic and implementation orientated

- Convene and chair Steering Committee meetings

2.4. IDP STEERING COMMITTEE

Composed of Departmental Managers, senior officials and a Councilor representing the Executive Committee, the IDP Steering Committee is a technical team tasked with the following responsibilities:

- Commission research studies

- Provide terms of reference for various planning activities

- Considers and comments on inputs from sub committees & study groups

- Considers and comments on inputs from provincial/ national sector departments & support providers

- Processes, summarizes and documents outputs

- Makes content recommendations

- Prepares, facilitates & document meetings

2.5 IDP REPRESENTATIVE FORUM

The IDP Representative Forum institutionalizes and guarantees representative participation in the IDP process and has the following responsibilities:

- Represent the interests of their constituents in the IDP process

- Provide an organizational mechanism for discussion, negotiation & decision making between stakeholders

- Ensure communication between all the stakeholders representatives

- Monitor the performance of the planning and implementation process

- MECHANISMS AND PROCEDURES FOR PUBLIC PARTICIPATION

Municipalities are required in terms of chapter 4 of the Municipal Systems Act to develop a culture of municipal governments that complements formal representative government with a system of participatory governments. Municipalities must therefore involve communities in the process of reviewing and implementing their Integrated Development Plans. Mutale Municipality has committed itself to insuring maximum participation of communities in the IDP Review/ Budget 2006/ 07 processes. The following participatory strategy will be applied throughout the process:

3.1. STAKEHOLDER ROLES IN PUBLIC PARTICIPATION

This has been outlined in 2.5 above.

3.2. REPRESENTATION OF UNORGANISED GROUPS

The plight of unorganized and marginalized groups will be represented through the participation of CBOs’, NGOs’ and provincial/ national government departments advocating their needs.

3.3. PARTICIPATORY MECHANISMS FOR THE DIFFERENT PLANNING PHASES.

This has been structured as follows:

ANALYSIS PHASE

- Ward Committee meetings

- Ward-based community participation meetings

- IDP Representative Forum meeting

STRATEGIES

- IDP Representative Forum workshop

PROJECTS

- Dialogue between Project Task Teams and project beneficiaries

- IDP Representative Forum meeting

INTEGRATION

- IDP Representative Forum meeting

APPROVAL

- Ward Committee meetings

- Ward-based community participation meetings

- IDP Representative Forum meeting

3.4. RESOURCES FOR PUBLIC PARTICIPATION

The Municipality will bear logistical costs in terms of venue, stationary, payment of facilitators and catering costs. Participants are responsible for their traveling costs.

- MECHANISMS AND PROCEDURES FOR ALLIGNMENT

Alignment within the review process serves as an instrument to synthesize and integrate the top-down and bottom-up planning processes between the three spheres of government. Mutale Municipality will ensure alignment as reflected in Vhembe District Municipality’s IDP Review Framework & Process Plan 2006/ 07.

- PROGRAMME AND BUDGET FOR THE PLANNING PROCESS

  - PHASE 1: ANALYSIS

| Planning activity | Task | Responsible Person | Time schedule | Participants | Required resources |
| --- | --- | --- | --- | --- | --- |
| Revision of status quo report | Date collection Upgrading of status quo report | Sector official | 1- 30 September 2005 | Sector Officials Steering Committee |  |
| 1.2 Community and stakeholders level analysis | Request community needs Reconciliation of status quo and community needs | Steering Committee, PIMS centre and Ward Councilors | 1- 30 September 2005 | Ward level stakeholders | R16 500.00 |
| 1.3 Budget instructions | Departments are issued with instruction to budget for 2006/07 | Finance | 1 – 30 September 2005 | Chief Financial Officer & all Heads of Departments |  |
| 1.4 Review of Municipal priority issues | Re-establishment of rep. forum & rep. forum workshop | Sector officials, steering committee. PIMS centre | 1 – 31 October 2005 | Steering Committee and IDP Rep. Forum | R2 000 R4 000 |
| 1.5 Confirmation of priority needs | Desktop | Steering Committee PIMS | 1 – 31 October 2005 | Steering Committee |  |
| TOTAL = R22 500 |

5.2 PHASE 2: STRATEGIES

| Planning Activity 1 | Task 2 | Responsible Person 3 | Time Schedule 4 | Participant 5 | Required resources & cost |
| --- | --- | --- | --- | --- | --- |
| 2.1 Review of view and objective | Steering committee meetings | Steering committee | 1 – 30 November 2005 | Steering committee members | R2 000 |
| Review of strategies | Creating strategic alternation Public debate on alternatives | Steering Committee sector officials & PIMS centre | 1 November – 31 December 2005 | IDP rep. forum, steering committee ward based stakeholders | R4 000 |
| 23. Project identification | Identification of projects | Steering committee, sector officials and PIMS Centre | 1 – 31 December 2005 | IDP rep. forum, steering committee and based stakeholders | R4 000 |
| SUB-TOTAL = R10 000.00 |

5.3	PHASE 3: PROJECTS

| Planning Activity 1 | Task 2 | Responsible Person 3 | Time schedule | Participants | Required recourses and cost |
| --- | --- | --- | --- | --- | --- |
| 3.1 Designing project proposals | Project Designs | Project task teams, PIMS and HOD techn. | 1 January – 28 February 2006 | Steering Committee | R2 000 |
| 3.2 Budget proposals from HOD | Submissions of proposals to Finance Department | HOD’S | 1 – 30 December 2005 | Finance Manager & HOD’s |  |
| 3.3 Preliminary Budget allocation | Budgeting | Project Task Teams, steering committee & HOD’s Finance & Technical | 1 – 28 February 2006 | Steering Committee PIMS, CFO |  |
| 3.4 Target group and Project partners participation in Project Planning | Ward based meetings | Project task, teams, steering committee, Exco & Ward Councilors | 1 – 28 February 2006 | Ward based structures | R8 000.00 |
| 3.5 Setting indicators for objectives | Workshop Desktop | Steering committee | 1 – 28 February 2006 | IDP rep. forum | R4 000.00 |
| SUB-TOTAL = R14 000.00 |

  - PHASE 4: INTERGRATION

| Planning Activity 1 | Task 2 | Responsible Person 3 | Time schedule | Participants | Required recourses and cost |
| --- | --- | --- | --- | --- | --- |
| 4.1 Screening of Draft Project proposals | Office work | Steering Committee & PIMS | 1- 28 February 2006 | Steering Committee | R2000 |
| 4.2 Integrating Projects & Programmes | Workshops | Project Task teams & sector officials | 1- 28 February 2006 | Steering Committee & IDP rep. forum | R4 000.00 |

  - PHASE 5: APPROVAL

| Planning Activity 1 | Task 2 | Responsible Person 3 | Time schedule 4 | Participants 5 | Required recourses and cost 6 |
| --- | --- | --- | --- | --- | --- |
| 5.1 Provide opportunity for comments from provincial / national government | Provincial / National comments | MEC for Local government Minister for DPLG | 1 – 31 March 2006 | Relevant stakeholders | R20 000.00 |
| 5.4 Adoption of Draft IDP/ Budget by Council | Council meeting | EXCO | 1 – 31 March 2006 | Council | R2 000.00 |
| 5.3 Incorporated Respond/comments from Province/ National departments Ward-based community consultative workshops | Office work & workshops Facilitate & conduct workshops | Steering Committee PIMS Councilors Ward committees Steering Committee | 1 – 30 April 2006 1 April – 31 May 2006 | Steering Committee & IDP forum Ward-based stakeholders | R4 000.00 R16 500.00 |
| 5.4 Adoption by Council | Council meeting | EXCO | 1 – 31 May 2006 | Council | R4 000.00 |
| TOTAL = R99 000.00 |

CHAPTER 3

3.  ANALYSIS

This chapter gives a description of the environment within which Mutale Local Municipality exists.

3.1. LOCATION

# Mutale Local Municipality is one of the four local municipalities comprising Vhembe District Municipality. It is situated in the far north eastern corner of the District. It covers an area of 2345. 8750 square kilometres. The Kruger National Park forms the eastern boundary of Mutale Local Municipality, with the great Limpopo River forming the north-eastern boundary. The Municipality’s strategic location affords it many opportunities for tourism development.

Mutale Local Municipality shares borders Musina Local Municipality to the north,  Makhado Local Municipality to the west and Thulamela Local Municipality  to the south. The Municipality is accessed R525 linking the Kruger National Park to Makhado and Musina through N1-national route. It can also be accessed the R linking Thohoyandou and Mutale.

The area is comprised of two towns, Mutale and Masisi as well as some 150 villages spread over seven tribal authorities. These settlements require considerable investment in service delivery related infrastructure since the area was traditionally neglected in this regard. Mutale Local Municipality is rich in history as it encapsulates many tribal wars, heritage assets such as Tshavhadinda caves and being home to the world’s biggest and oldest Baobab tree situated at Zwigodini village.

### 3.2. DEMOGRAPHICS

| Ward | Population | % of total population |
| --- | --- | --- |
| 1 | 9 827 | 10.26 |
| 2 | 7 712 | 8.05 |
| 3 | 9 175 | 9.58 |
| 4 | 7 091 | 7.40 |
| 5 | 6 111 | 6.46 |
| 6 | 11 573 | 12.08 |
| 7 | 8 584 | 8.96 |
| 8 | 12 109 | 12.65 |
| 9 | 7 513 | 7.84 |
| 10 | 9 830 | 10.26 |
| 11 | 6 187 | 6.46 |
| TOTAL | 95 712 | 100.00 |

### Registered voters per ward

| Ward 1 | 4222 |
| --- | --- |
| Ward 2 | 3114 |
| Ward 3 | 3473 |
| Ward 4 | 3661 |
| Ward 5 | 3453 |
| Ward 6 | 3900 |
| Ward 7 | 3356 |
| Ward 8 | 4123 |
| Ward 9 | 3372 |
| Ward 10 | 3371 |
| Ward 11 | 3294 |
| Total | 39 339 |

#### 3.3. ACCESS TO SERVICES:

| SERVICE | 1996(13 113 households) |  | 2001 (17 645 households) |  | 2005 (20 795 households) |
| --- | --- | --- | --- | --- | --- |
|  | Basic and above | Below basic |  | Basic and above | Below basic |  | Access (RDP Standard) | No Access (Below RDP Standard) |
| Water | 9 474 | 3 639 |  | 13 796 | 3 848 |  | 4 343 | 16 980 |
| Sanitation | 7 540 | 5 573 |  | 9 831 | 7 813 |  | 3 583 | 17 741 |
| Electricity | 931 | 12 182 |  | 7 280 | 10 365 |  | 9 574 | 11 750 |
| Refuse Removal | 224 | 12 889 |  | 1 067 | 16 578 |  | 900 | 20 953 |
| Housing | 4 316 | 8 799 |  | 9 447 | 8 195 |  | 12 865 | 8 459 |

## Population receiving Free Basic Services

| FBS | Total households | Total indigent households | Household/Indigent served | % Served |
| --- | --- | --- | --- | --- |
| FBW | 20 795 | 14 262 | 20 | 0% |

| FBS | Households R800 and less monthly income | TOTAL HOUSEHOLDS RECEIVING FREE BASIC ELECTRICITY | BUDGET ALLOCATION (2004/05) | TOTAL EXPENDITURE (2004/05) |
| --- | --- | --- | --- | --- |
| FBE | 9 574 | 772 | R 874 552 00 | 146 526 |

| FBS | POPULATION 2001 | GENERATED WASTE 2004 (TONS) | % POPULATION RECEIVING SERVICE | %POPULATION NOT RECEIVING |
| --- | --- | --- | --- | --- |
| FBR | 78922 | 2500 | 7% | 93% |

3.4 MUNICIPAL WIDE PRIORITY ISSUES

| 1 | WATER & SANITATION | A |
| --- | --- | --- |
| 2 | ELECTRICITY AND LIGHTS | A |
| 3 | HOUSING AND LAND | A |
| 4 | ROADS AND STORMWATER DRAINAGE | A |
| 5 | WASTE MANAGEMENT | A |
| 6 | FREE BASIC SERVICES | A |
| 7 | AGRICULTURAL DEVELOPMENT | A |
| 8 | TOURISM | B |
| 9 | INDUSTRIES AND SKILLS DEVELOPMENT | A |
| 10 | SPORT AND RECREATION | B |
| 11 | MINING | C |
| 12 | SMME SUPPORT & TRADE PROMOTION | A |
| 13 | EDUCATION AND TRAINING | A |
| 14 | HEALTH AND SOCIAL DEVELOPMENT | A |
| 15 | SAFETY AND SECURITY | B |
| 16 | FINANCIAL VIABILITY | A |
| 17 | MUNICIPAL TRANSFORMATION | A |
| 18 | GOOD GOVERNANCE | A |

A: represents high priority

B: represents midium priority

C: represents low prioroty

These priority needs, together with the core operational and management functions (requirements) form the basis of the IDP process and assisted the Representative Forum in Identifying the important development priorities to be addressed during the next five years.

The dynamics underlying each of these priority issues will be discussed acccording to this discussion  framework in more detail below.

3.5. ANALYSIS OF PRIORITY ISSUES

3.5. 1. INFRASTRUCTURE AND SERVICES

As depicted above, the Municipality is characterised by huge  service backlogs. This can mainly be attributed to the following factors:

- Inadequate infrastructure. The municipal area received mimimal investment in service related infrastructure from government pre 1994. The little infrastructure in place was also poorly maintained to such an extent that it can not cope with the current demand for services. It is unfortunate that the culture of non maintance of service delivery infrastructure continued post 1994. A snap shot view of the budgets of Mutale Municipality over the last five years demonstrate that the maintanance of infrastructure is not prioritised.

- Poor planning, implementation and monitoring of service delivery. This problem affect key services such as water, sanitation, electricity and roads. The mismanagement of water services in particular poses serious sustainability challenges in the provision of the service. Meter reading is done on an ad hoc basis and commnities, save for Mutale Town residents are not billiled for the consumption of water. Other service delivery problems include illegal dumping and disposal of waste and poorly maintained roads and streets.

All this issues have a negative impact on the quality and standard of the service provided and fuel the growing perception o service delivery. More in-depth analysis need to be conducted on the causes and effects of these problems.

3.5.2. ECONOMIC DEVELOPMENT

### Agricultural Development

Extensive farming (crop and livestock) is more prevalent in the eastern areas.

#### Core issues

The underlying causes of agricultural development realities as well as the resulting core issues that need to be addressed are summarized in the table below:

| CORE ISSUES | DESCRIPTION |
| --- | --- |
| Very little value adding taking place. | The fact that very limited value adding is taking place places a large burden on the agricultural sector and makes the region very vulnerable to factors influencing agriculture. Many of these factors cannot be controlled such as the weather and prices. To limit the vulnerability to markets it is important to add value to products before it is exported out of the municipality. |
| Good agriculture potential. | The area has proven that it has good agricultural potential. This should be exploited, but as mentioned above the necessary supporting sectors will have to be developed before the agricultural sector can expand. |
| Role of emerging farmers. | Emerging farmers need support from existing commercial farmers and the Department of Agriculture in terms of knowledge and information sharing. The agricultural sector should be made more accessible to emerging farmers. |

### Tourism Development

The table below provides a brief overview of tourist attractions and facilities within the area of jurisdiction of Mutale;

| Tourist Attraction | Location | Exclusiveness |
| --- | --- | --- |
| Baobab Tree | Zwigodini Village | Biggest tree in Africa |
| Domboni Caves | Domboni Village | Hiding place during Tribal wars |
| Sagole Spa | Tshipise | Warm baths and accommodation |
| Nwanedi Nature Reserve | Folovhodwe | Animal viewing & accommodation |
| Tourist Attraction | Location | Exclusiveness |
| Makuya Park | Adjacent to Kruger National Park | Animal viewing & camping facilities |

#### These natural wonders are however not easily accessible due to the poor road infrastructure of the Municipality. A lack of reliable energy and potable water also hinder the growth of the tourism industry. No database of all tourism centres exist, resulting in these centres not properly developed and marketed

#### Core issues

The underlying causes of the abovementioned realities as well as the resulting core issues that need to be addressed are summarized in the table below:

| CORE ISSUES | DESCRIPTION |
| --- | --- |
| Co-ordination of efforts. | To maximise the potential of tourism within the area it is important that there is a coordinated approach in planning and developing the tourism industry. This will limit duplication and strengthen existing efforts. |
| Cultural tourism attraction | The cultural diversity activities of the area, coupled to the increase in international cultural interest should be exploited as integral part of the tourism effort. |
| Accessibility of facilities. | Accessibility refers to both physical accessibility as well as socio-economic affordability. |

### Light Industries & SMME’s

No major industrial developments are taking place in Mutale. The promotion of agri-processing plants and other value adding industries should be encouraged in order to diversify the economy of the area. Currently there is an established facility available for the development arts and crafts. The promotion of skills development programmes locally are a crucial part of industrial and general employment stimulation. The utilization of existing facilities (e.g. land, buildings, and railways) for industrial promotion purposes is important.

A Training College for Traffic Officials is situated in Mutale and is utilized on a regular basis.

Small to medium sized enterprises within the municipality operate in isolation and without some sense of common purpose. There is no existing database of SMME’s available. The viability of these businesses is also questionable, as the operation methods generally do not comply with modern practices of operating businesses.

Core issues

The underlying causes of the abovementioned realities as well as the resulting core issues that need to be addressed are summarized in the table below:

| CORE ISSUES | DESCRIPTION |
| --- | --- |
| Low market potential | Consumer price indexes should be targeted to stimulate local markets and expenditure. |
| Cost of infrastructure and services. | Start with provision of infrastructure on a small scale |
| Organized and mobile labour force. | A large contribution to the high unemployment rates are the fact a major portion of the potential labour market is unskilled or unstructured, making it difficult to access information and opportunities which might arise. |
| Skilled labour force. | Skilled labourers are leaving the area constantly and should be engaged in the LED process to retain them. Unskilled labourers should also be trained locally for local potentials and needs. |

3.5.3. SOCIAL DEVELOPMENT

### Health

Emergency services associated with health care are given in the table below:

| Munici pality | Hospital | Health Clinics | Health Centre | HIV/Aids Desk | Mobile Clinics | Oral Health | Nutrition Program | Emer- gency Service | Radio graphic Service |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mutale | 0 | 17 | 1 | 0 | 3 | 0 | y | 1 | 0 |

The main community needs are also summarized below:

- Ambulance Services

Ambulance service serves a wide area within the region and the operating cost is escalating constantly.

- Fire Fighting Service

Fire Fighting Service is rendered by the District Municipality. A proper fire station has been erected at Mutale by the District Municipality. Local residents have to be trained in fire fighting.

- Hospital

Hospitals are located in Thulamela, which is 100km away from the residents. The services at the local health clinics are not up to standard. A fully equipped hospital is urgently needed in Mutale.

- HIV/AIDS Desk

There is a significant increase in HIV/AIDS and TB occurrence. A counseling/help desk is needed in each clinic where the community can be guided and counseled

- Malnutrition

Malnutrition occurs, especially among young children. Nutrition programs must be initiated by the municipality and the Dept of Health

### Education

Education is a crucial part of higher provincial structures and the role of the municipality is only seen as one of supporting SGBs, liaising with the Department of Education, assisting in the provision of land and facilities and promoting regional policies aimed at maintaining a high quality of education of both the younger learners as well as adults and the labor market.

There are 83 Primary Schools and 25 Primary and Secondary schools in the Mutale area, which are predominantly government funded and operated.

There is no tertiary facility. Due to the agricultural characteristic of the area, as well as the lack of education facilities in the rural areas, the development of a quality agricultural school for the region should be investigated. The establishment of tertiary institution should also be investigated and facilitated.

ABET projects within the municipal area are non-functional, mainly because of budgetary constraints and lack of interest.

#### Core issues

The underlying causes of the abovementioned realities as well as the resulting core issues that need to be addressed are summarized in the table below:

| CORE ISSUES | DESCRIPTION |
| --- | --- |
| Maintain high level of pass rate | All efforts should be made to maintain the increased level of pass rate at schools in the area. |
| Discipline of learners and educators. | Measures should be put in place to maintain the discipline Mechanisms should be considered to address discipline of both learners and educators. |
| Parent Involvement. Improve discipline. | Parent involvement in the education of their children, as well as the general management, maintenance and functioning of the school and its facilities should improve education standards. |
| Adult literacy. | High levels of adult illiteracy occur within the various areas of the community and this in return increases poverty and health risks due to ignorant residents. The local ABET programme will have to be expanded and promoted to address this issue. |
| Tertiary education opportunities. | The rural areas as well as smaller towns, do not have direct access to local tertiary satellite education services. This results in a rapid decline in the higher education levels within the area, as well as an outflow of youth seeking education opportunities in major centres. Local access to student loans, satellite services and information could remedy this situation. |

### Public safety and security

As would be expected in smaller towns, the general crime rate is lower than other urban nodes in the province

The ability to combat crime is hampered through a lack of proper communication, a lack of information from community members and under resourced police stations. It is believed that a greater community involvement through existing structures should address most of these problems.

#### Core issues

The underlying causes of the abovementioned realities as well as the resulting core issues that need to be addressed are summarized in the table below:

| CORE ISSUES | DESCRIPTION |
| --- | --- |
| Community co-operation. | Intelligent policing is dependent on the input of the entire community in terms of both resources and basic information. Currently these efforts of community involvement are hampered by intimidation and the fact that all role players are not involved in a structured system. The Sectoral Policing Forum will address these problems. |
| Capacity of local stations. Distances | The capacity of the SAPS stations is limited due to a lack of proper equipment and vehicles and sufficient numbers of police officers. This problem is caused by a lack of financial resources. |

### Sport and recreation

The area lacks adequate Sports and Recreational facilities. There is only one Community Hall, situated in Mutale and which must cater for all residents. There are mostly inadequate grounds to use for soccer fields throughout the municipal area. The youth are generally not exposed to other sporting codes.

5.4. INSTITUTIONAL DEVELOPMENT

With regards to institutional development, the following issues were identified:

- High debt level: The municipality is owed in access of R2M in property rates and service charges. About 65% of this debt is owed by government departments.

- Skills levels: The staff’s productivity levels and quality of its work is generally substandard. This is due to the insufficient and at times lack of relevant skills within the Municipality.

- Limited revenue base: This can mainly be attributed to the prevailing land tenure system as villages could not be traditionally billed as these settlements are located in communal land. The Implementation Plan, prepared in terms of the provisions of the Property Rates Act, 2003 indicates that these properties will only be billed in the financial year 2008/ 09. As such, the Municipality is only receiving rates and taxes from businesses and public institutions. Trading services like water and electricity are, in terms of the current assignment of powers and functions residing with Vhembe District Municipality and Eskom respectively. This state of affairs further paralyses the Municipality’s ability to collect much required revenue that will ensure its sustainability, in financial terms.

- Strategic and structural misalignment: The Municipality’s Organisational Structure is not based on and aligned to its Integrated Development Plan. This has resulted in the ineffective deployment of human and other resources.

- Inadequate systems, policies and procedures: There is a need for the development of a cohesive integrated policy and procedure manual.

CHAPTER 4

4. STRATEGIES

| Council’s vision | “A developmental municipality that ensures sustainable economic growth & equitable service delivery”. |
| --- | --- |
| Objectives and strategies |
| Number of objectives |  |
| Keyword list of priority issues | What are the objectives per priority issue, including time and quantitative measures? | List the keywords of the strategies developed to meet the objectives. |
| Water & Sanitation | Ensure that all residents have access to clean potable water at RDP level by 2010 in line with National Government’s 2014 Vision. Extend billing to all areas with metered connections by 2008. Ensure that all households have access to sanitation that complies with at least minimum RDP requirements by 2010. | Building of water services infrastructure Provision of individual connections through the implementation of an approved water tariff structure Review of Water Sector Plan Tankering of villages with critical water shortages Provision of VIP toilets to households |
| Electricity & Lights | Ensure that all villages are connected to grid electricity by 2011 in line with National Government’s 2014 vision. Ensure that indigent households are provided with free basic electricity. | Reticulate areas with bulk supply using ESKOM electrification programme. Subsidization of indigent households |
| Roads & Stormwater | Ensure that all roads are properly maintained and are in a good passable condition by June 2011. Ensure road safety within the Municipality. | Development & implementation of a Road Master Plan. Roads construction Establishment of a Local Transport Forum |
| Land &Housing | Ensure the adherence of housing development to the provisions of Sustainable Human Settlements as contained in Agenda 21 & Habitat Agenda Facilitate the provision of low cost housing to impoverished communities | Engagement with stakeholders on land reform Identification of potential housing subsidy recipients Demarcation and servicing of land for housing development Development & Implementation of Housing Development Plan |
| Waste Management | Ensure that waste management service is extended to all settlements by 2011. Ensure that free basic refuse removal is extended to indigents in serviced settlements | Development & Management of a permitted Land Fill Site Acquisition of suitable waste/ refuse removal equipments |
| Agricultural Development | To add value to agricultural products in order to ensure employment & income generation from the agricultural sector. Ensure that the agricultural sector is properly organized. | Development of training programmes aimed at emerging farmers Source funding for agricultural projects |
| Tourism | To promote local tourism in a manner that will attract investors & tourists to the Municipality. Ensure the development of tourism support infrastructure and services to enhance accessibility & ensure competitive edge. | Work in close cooperation with Limpopo Tourism and Parks Board to market the local tourism experience nationally & internationally. Identification of emerging tourism initiatives & source funding on their behalf. Support local tourism entrepreneurs through capacity building programmes |
| Industries & Skills Development | Promote industrial development within the two identified municipal growth points To assist in the mobilization of local labour force through skills development opportunities | Investor attraction through offering tax incentives & rebates on service charges Establishment of a local trading centre Job creation & skills development through the implementation of Expanded Public Works Programme |
| SMME Support | Ensure the establishment and management of business support centre | Technical business advice Capacity building programme for LED stakeholders |
| Health | Rehabilitation of all health facilities by 2011. Ensure the extension of social security grants to all qualifying persons. | Renovation and equipment of clinics. |
| Education | Promotion of adult learning. Ensure provisions of adequate educational facilities | Revitalization of ABET centres in conjunction with Provincial Education Department. Classroom provision |
| Sports | Ensure community access to sporting facilities. | Erection of sporting facilities in targeted areas. |
| Safety & security | Promotion of community involvement in policing. | Community information sharing through Sectoral Policing Forum. |
| Financial Viability | Ensure maximum collection of revenue. | Implement Credit Control Policy Facilitate debt collection programme |
| Municipal Transformation | Provision of support system and ensure institutional readiness to tackle the development challenge | Review and implementation of policies, procedure and systems |
| Good governance | Ensure that communities and other stakeholders participate in Municipal affairs | Functional ward committee system |

CHAPTER 5

5. PROJECTS

| No. | Sector | Project Description | Funding | Location | 2006/2007 Budget in Rand | 2007/2008 Budget in Rand | 2008/2009 Budget in Rand | 2009/2010 Budget in Rand | 2010/2011 Budget in Rand | Total Project cost | Time Frame | Priority |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 6-7/01 | Water | Drill borehole, construction of reservoir & pipeline at RDP level | MIG | Tshivhongweni | 2 500 000 |  |  |  |  |  |  |  |
| 6-7/02 | Water | Construction of reservoir & reticulation at RDP level and boaster pump at Mavhode. | MIG | Mavhode, Madatshitshi, Tshamulungwi, Mafhohoni, Goma | 6 000 000 |  |  |  |  |  |  |  |
| 6-7/03 | Water | Construction of reservoir & reticulation at RDP level | MIG | Guyuni, Khunguni | 3 500 000 |  |  |  |  |  |  |  |
| 6-7/04 | Water | Construction of bulk pipeline & reticulation at RDP level | MIG | Zwigodini, Madifha | 2 000 000 |  |  |  |  |  |  |  |
| No. | Sector | Project Description | Funding | Location | 2006/2007 Budget in Rand | 2007/2008 Budget in Rand | 2008/2009 Budget in Rand | 2009/2010 Budget in Rand | 2010/2011 Budget in Rand | Total Project cost | Time Frame | Priority |
| 6-7/05 | Water | Borehole, Construction of reservoir & pipeline at RDP level | MIG | Tshenzhelani | 2 000 000 |  |  |  |  |  |  |  |
| 6-7/06 | Water | Construction of reservoir & pipeline at RDP level | MIG | Tshikuyu, Dovho, Duluthulu, Bende Mutale & Masisi village | 7 000 000 |  |  |  |  |  |  |  |
| 6-7/07 | Water | -Construction of reservoir & pipeline at RDP level. -Construction of package and treatment plant. | MIG | Tshivaloni, Mutele A& B, Sanari, and Mukoma villages. | 2 000 000 5 000 000 |  |  |  |  |  |  |  |
| 6-7/08 | Water | Construction of reservoir & pipeline at RDP level | MIG | Mukununde, Tshamutavha ,Maramanzhi | 2 000 000 |  |  |  |  |  |  |  |
| 6-7/09 | Water | Rehabilitation of Makuya RW S | MIG | Makuya | 2 000 000 |  |  |  |  |  |  |  |
| No. | Sector | Project Description | Funding | Location | 2006/2007 Budget in Rand | 2007/2008 Budget in Rand | 2008/2009 Budget in Rand | 2009/2010 Budget in Rand | 2010/2011 Budget in Rand | Total Project cost | Time Frame | Priority |
| 6-7/10 | Water | Rehabilitation of Gwangwatini RWS | MIG | Gwangwatini | 1 500 000 |  |  |  |  |  |  |  |
| 6-7/11 | Water | Reticulation & pipeline at RDP level Phase 2 | MIG | Tshiungani, Masea, Matshena | 1 500 000 |  |  |  |  |  |  |  |
| 6-7/12 | Water | Reticulation & pipeline at RDP level Phase 2 | MIG | Tshixwadza | 2 000 000 |  |  |  |  |  |  |  |
| 6-7/13 | Water | Rehabilitation of existing infrastructure | MIG | Khakhu | 3 000 000 |  |  |  |  |  |  |  |
| 6-7/15 | Water | Extension of bulk water line phase | MIG | Dzimauli - Tshixwadza | 7 000 000 |  |  |  |  |  |  |  |
| No. | Sector | Project Description | Funding | Location | 2006/2007 Budget in Rand | 2007/2008 Budget in Rand | 2008/2009 Budget in Rand | 2009/2010 Budget in Rand | 2010/2011 Budget in Rand | Total Project cost | Time Frame | Priority |
| 6-7/16 | Water | Refurbishment of water treatment plant Phase 2 X | MIG | Mutale RWS | 5 000 000 |  |  |  |  |  |  |  |
| 6-7/17 | Sanitation | Construction of VIP- 1050 | MIG | Matshavhawe x 24 Gogogo x 24 Tshibvumo x 24 Ngalavhani x 23 Gwangwatini x 23 Tshandama RDP House x 187 Phalama x 24 Maheni x 24 Makwilidza x 24 Mukovhawabale x 24 Shakadza x 24 Gumela x 24 Tshitanzhe x 24 Musunda x 24 Masea x 24 Bale x 24 Matatani x 24 Gwakwani x 24 Tshivaloni x 24 Tshikuyu x 24 Khavhambe x 24 Masisi RDP House 385 | 3150 000.00 |  |  |  |  |  |  |  |
| 6-7/18 | Electricity | Electrification of 950 households | Own funding | Mutale Extension | 2 000 000.00 |  |  |  |  |  |  |  |
| No. | Sector | Project Description | Funding | Location | 2006/2007 Budget in Rand | 2007/2008 Budget in Rand | 2008/2009 Budget in Rand | 2009/2010 Budget in Rand | 2010/2011 Budget in Rand | Total Project cost | Time Frame | Priority |
| 6-7/19 | Electricity | Electrification of 150 households | Eskom | Madadani | 750 000 |  |  |  |  |  |  |  |
| 6-7/20 | Electricity | Electrification of 80 households | Eskom | Mapate | 400 000 |  |  |  |  |  |  |  |
| 6-7/21 | Electricity | Electrification of 150 households | Eskom | Phalama Extension | 750 000 |  |  |  |  |  |  |  |
| 6-7/22 | Electricity | Electrification of 180 households | Eskom | Tshanzhe | 900 000 |  |  |  |  |  |  |  |
| 6-7/23 | Electricity | Electrification of 200 households | Eskom, VDM | Folovhodwe | 1 000 000 |  |  |  |  |  |  |  |
| 6-7/24 | Electricity | Electrification of 150 households | Kumba Resources | Mukomawabani | 750 000 |  |  |  |  |  |  |  |
| No. | Sector | Project Description | Funding | Location | 2006/2007 Budget in Rand | 2007/2008 Budget in Rand | 2008/2009 Budget in Rand | 2009/2010 Budget in Rand | 2010/2011 Budget in Rand | Total Project cost | Time Frame | Priority |
| 6-7/25 | Land & Housing | Construction of 350 units | DLGH | Bale X 13; Lwathudwa X10; Tshiungani 2 X 13; Maramanzhi X 18; Tshandama X 12; Lukau X 10; Phalama X 9; Khunguni X 2; Mulodi X 15; Matshetshete X 9; Tshitunguni X 8; Sigonde X 10; Tshenzhelani X 10; Gumela X 10; Ngalavhani/ Gwangwatini X 10, Guyuni 1 & 2 X 10; Pile X 3; Tshapasha X 10, Dzamba X 11; Mapuloni X 1; Gogogo X 11; Tshivhongweni X 11; Zwigodini X 10; Matatani X 8; Gwakwani X 4; Muraluwe – Tshipale X 2; Madadani X 10; Tshithuthuni X 10; Madzivhanani X 10; Tshitambe X 7; Musunda X 3; Tshitanzhe X 3; Ngalavhani X 4; Mphagani X 10; Madzwororo X 5; Tshifume X 5, Maholoni X 16, Khavhambe X 10. | 11 917 150 | 400 units X 14 300 580 | 450 X 16 088 153 |  |  |  |  |  |
| 6-7/26 | Roads | Construction of tarred road | RAL | Shadani - Masisi | 60 000 000 |  |  |  |  |  |  |  |
| 6-7/27 | Roads | Construction of tarred road | RAL | Shakadza, Big Tree, Dambale, Bale. | Not yet confirmed |  |  |  |  |  |  |  |
| 6-7/28 | Roads | Construction of tarred road | RAL | Tshandama - Siloam | Not yet confirmed |  |  |  |  |  |  |  |
| 6-7/29 | Roads | -Construction of tarred road | RAL | Muswodi – Folovhodwe | Not yet confirmed |  |  |  |  |  |  |  |
| 6-7/30 | Roads | Construction of gravel road | RAL | Shakadza - Tshirunzini |  |  |  |  |  |  |  |  |
| 6-7/31 | Roads | Upgrading of gravel road into graft sil. | RAL | Muswodi – Muraluwe | Not yet confirmed |  |  |  |  |  |  |  |
| 6-7/32 | Roads | Construction of gravel road (phase 2). | MIG | Mutale - Khunguni | Not yet confirmed |  |  |  |  |  |  |  |
| 6-7/33 | Roads | Construction of bridge & access road | MIG | Dotha | Not yet confirmed |  |  |  |  |  |  |  |
| 6-7/34 | Waste Management | Construction of permitted land fill site | MIG/ VDM | Gundani | 3 329 000 |  |  |  |  |  |  |  |
| 6-7/35 | Water | Construction of dam | Dwaf | Mutale river | Not yet confirmed |  |  |  |  |  |  |  |
| No. | Sector | Project Description | Funding | Location | 2006/2007 Budget in Rand | 2007/2008 Budget in Rand | 2008/2009 Budget in Rand | 2009/2010 Budget in Rand | 2010/2011 Budget in Rand | Total Project cost | Time Frame | Priority |
| 6-7/36 | LED | Construction of Cultural village & Tourism Centre | Kumba Resources | Bennde Mutale | 430 000 |  |  |  |  |  |  |  |
| 6-7/37 | LED | Construction of Eco - Tourism Centre | VDM | Duluthulu | 955 000 |  |  |  |  |  |  |  |
| 6-7/38 | LED | Capacity building & support to LED stakeholders | EU - LGSF | Mutale Municipal area | 841 020 |  |  |  |  |  |  |  |
| 6-7/39 | LED | Business support Service Centre | EU - LGSF | Mutale Municipal area | Not yet confirmed |  |  |  |  |  |  |  |
| 6-7/40 | LED | Youth Advisory Centre staffing. | Umsobomvu | Tshandama Arts & craft center | 300 000 |  |  |  |  |  |  |  |
| 6-7/41 | LED | Fruit Market Stalls | DEDET | Makuya MPCC | Not yet confirmed |  |  |  |  |  |  |  |
| 6-7/42 | LED | Support to Arts & Crafts Cooperative | ILO | Mutale | 380 000 |  |  |  |  |  |  |  |
| 6-7/43 | LED | Livestock Infrastructure/ Grazing Camp | Dept. of Agriculture | Manenzhe | 125, 000 |  |  |  |  |  |  |  |
| 6-7/44 | LED | Livestock Infrastructure/ Grazing Camp | Dept. of Agriculture | Tshamutavha | 125, 000 |  |  |  |  |  |  |  |
| 6-7/45 | LED | Livestock Infrastructure/ Grazing Camp | Dept. of Agriculture | Tshibvumo | 125, 000 |  |  |  |  |  |  |  |
| 6-7/46 | LED | Livestock Infrastructure/ Grazing Camp | Dept. of Agriculture | Vuvha | 125, 000 |  |  |  |  |  |  |  |
| 6-7/47 | LED | Livestock Infrastructure/ Grazing Camp | Dept. of Agriculture | Gogogo | 125, 000 |  |  |  |  |  |  |  |
| 6-7/48 | LED | Emerging farmers programme | Dept of Agriculture | Mutale | 200 000 |  |  |  |  |  |  |  |
| 6-7/49 | LED | Micro enterprise | Dept of Agriculture | Mataulu | 174 713 |  |  |  |  |  |  |  |
| 6-7/50 | LED | Revitalization of irrigation schemes | Dept of Agriculture | Folovhodwe | 4 483 167 |  |  |  |  |  |  |  |
| 6-7/51 | LED | Revitalization of irrigation schemes | Dept of Agriculture | Klein Tshipise | 4 081 167 |  |  |  |  |  |  |  |
| 6-7/52 | LED | Revitalization of irrigation schemes | Dept of Agriculture | Sanari | 4 591 167 |  |  |  |  |  |  |  |
| 6-7/53 | LED | Revitalization of irrigation schemes | Dept of Agriculture | Rambuda | 5 662 167 |  |  |  |  |  |  |  |
| 6-7/54 | INSTITUTIONAL | Establishment of PMU. | MIG | Mutale | 171 000 |  |  |  |  |  |  |  |
| 6-7/55 | Education | Construction of comprehensive school. | Dept. of Education | Thengwe sec. school x 40 classrooms, 1 admin block, 3 laboratories and 2 computer center and a sports facility. | 20 000 000 |  |  |  |  |  |  |  |
| 6-7/56 | Sports, Arts & Culture | Palisade fence | Own fund | Tshixwadza | 200 000 |  |  |  |  |  |  |  |
| 6-7/57 | Sports, Arts & Culture | Extent ion of town hall to include indoor sports centre | N L D F | Tshilamba | Not yet confirmed |  |  |  |  |  |  |  |
| 6-7/58 | Sports, Arts & Culture | Registering cooperatives and skills training | ILO. | All wards | 18400 |  |  |  |  |  |  |  |
| 6-7/59 | Health | Upgrading of Mutale Health center into a hospital | Dept. of Health and Social Dev. | Tshilamba | Not yet confirmed |  |  |  |  |  |  |  |
| 6-7/60 | Traffic | Construction of MV test pit | Own fund | Tshilamba Extension | 2 500 000.00 |  |  |  |  |  |  |  |
| 6-7/61 | Disaster management | Purchase of Disaster tents | Own fund | Municipal office | 100 000.00 |  |  |  |  |  |  |  |
| 6-7/62 | Traffic | Purchase of fire arms. | Own fund | Municipal office | 50 000.00 |  |  |  |  |  |  |  |
| 6-7/63 | Waste management | Purchase of refuse containers | Own fund | Tshilamba/Masisi | 50 000.00 |  |  |  |  |  |  |  |
| 6-7/64 | Technical | Construction of streets lights | Own funding | Tshilamba | 500 000.00 |  |  |  |  |  |  |  |
| 6-7/65 | Sports | Construction of museum | Sports, A & Culture and Environmental affairs | Tshilamba | Not yet confirmed. |  |  |  |  |  |  |  |
| 6-7/66 | Corporate | Purchase of office equipment | Own fund | Tshilamba | 500 000.00 |  |  |  |  |  |  |  |
| 6-7/67 | Sports | Construction of stadium phase 1 | Own funding/Donors | Tshilamba | Not yet confirmed |  |  |  |  |  |  |  |
| 6-7/68 | Sports | Construction of Indigenous game centre | Sports, A& C | Tshilamba | 500 000.00 |  |  |  |  |  |  |  |
| 6-7/69 | Technical | Demarcation of residential sites | DLGH | Tshipise x100, Musunda x 100, Bale x100, Lurangwe x 100, Mafukani x 100, Maholoni x 100, Mapakoni x 100,Tshapasha x100,Maheni x 100, Tshilavulu x 100. | Not yet confirmed |  |  |  |  |  |  |  |
| 6-7/70 | Technical | Construction of a tower | Trade & Industry | Tshilamba | Not yet confirmed |  |  |  |  |  |  |  |
| 6-7/71 | Sports | Upgrade of playground | Own funding | Phalama | 300 000 |  |  |  |  |  |  |  |
| 6-7/72 | INSTITUTINAL | IDP Review/ Budget Process 07/ 08 | MSIG |  | 294 000 |  |  |  |  |  |  |  |
| 6-7/73 | INSTITUTIONAL | Ward Committee Capacity Building | MSIG |  | 90 000 |  |  |  |  |  |  |  |
| 6-7/74 | INSTITUTIONAL | Compilation of Valuation Roll | MSIG |  | 350 000 |  |  |  |  |  |  |  |
| 6-7/75 | INSTITUTIONAL | Implementation of WSP | Own |  | 500 000 |  |  |  |  |  |  |  |
| 6-7/76 | Social | Municipal Social Crime Prevention Programme | Safety & Security |  | 160 000 |  |  |  |  |  |  |  |
| 6-7/77 | Social | Project five star of the cells | Safety & Security, SAPS | Mutale Police Station |  |  |  |  |  |  |  |  |
| 6-7/78 | Institutional | Formation of Transport Forum | Roads & Transport |  | 18 750 |  |  |  |  |  |  |  |
| 6-7/79 | Transport | Animal Drawn Carts | Roads & Transport |  | 70 000 |  |  |  |  |  |  |  |
| 6-7/80 | Transport | Bicycle project | Roads & Transport |  | 1 000 000 |  |  |  |  |  |  |  |
| 6-7/81 | Transport | Taxi Recapilization | Roads and Transport |  | 6 750 000 |  |  |  |  |  |  |  |
| 6-7/82 | Education | Construction of 8 classrooms | Education | Khavhambe Primary School | 123 000 | 123 000 |  |  |  |  |  |  |
| 6-7/83 | Education | Construction of 4 classrooms | Education | Ladzani Primary School | 61 500 | 61 500 |  |  |  |  |  |  |
| 6-7/84 | Education | Construction of 12 classrooms | Education | Karel Ngigideni Primary School | 184 500 | 184 500 |  |  |  |  |  |  |
| 6-7/85 | Education | Construction of 8 classrooms | Education | Masisi Primary School | 123 000 | 123 000 |  |  |  |  |  |  |
| 6-7/86 | Education | Construction of 8 classrooms | Education | Tshanzhe Primary School | 123 000 | 123 000 |  |  |  |  |  |  |
| 6-7/87 | Education | Construction of 8 classrooms | Education | Tshipise Primary School | 123 000 | 123 000 |  |  |  |  |  |  |
| 6-7/88 | Education | Construction of 4 classrooms | Education | Tshikuyu Primary School | 61 500 | 61 500 |  |  |  |  |  |  |
| 6-7/89 | Education | Construction of 4 classrooms | Education | Tshivhambe Primary School | 61 500 | 61 500 |  |  |  |  |  |  |
| 6-7/90 | Education | Construction of 4 classrooms | Education | Mangwele Primary School | 61 500 | 61 500 |  |  |  |  |  |  |
| 6-7/91 | Education | Construction of 8 classrooms | Education | Guyuni Primary School | 123 000 | 123 000 |  |  |  |  |  |  |
| 6-7/92 | Education | Construction of 8 classrooms | Education | Tshikundamalema Secondary School | 123 000 | 123 000 |  |  |  |  |  |  |
| 6-7/93 | LED/ Tourism | Infrastructure Upgrade | Limpopo Tourism & Parks Board | Makuya Park | 4 525 000 |  |  |  |  |  |  |  |
| 6-7/94 | LED/ Tourism | Infrastructure Upgrade | Limpopo Tourism & Parks Board | Nwanedi Park | 3 720 000 |  |  |  |  |  |  |  |

CHAPTER 6

- INTEGRATION

Sector plans and programmes must in terms of Section 26(d) of the Local Government: Municipal System Act, 2000 (Act no. 32 of 2000) be aligned to national/ provincial plans and planning requirements as legislated. The following sector plans are included in this review as annexures:

- 5 Year Financial Plan			Annexure A

- Disaster Management Plan		Annexure B

- Integrated HIV/ AIDS Programme		Annexure C

- Integrated Institutional Plan		Annexure D

- Performance Management System	Annexure  E

- Spatial Development Framework             Annexure F

- Local Economic Development Strategy	Annexure G

CHAPTER 7

- CONCLUSION

The 2006/ 07 IDP Review departs drastically from past practice. A broad range of role players and resource person contributed. This review has brought forth issues that still need further and focused attention in the short to mid term. Based of current facts and realities, the Council is considering its options regarding the status of the current IDP.

# Text boxes

SOCIAL DEVELOPMENT

Health & Welfare

Education and training

Safety & Security

Sports & Recreation

INSTITUTIONAL DEVELOPMENT

Financial Viability

Municipal Transformation

Good Governance

ECONOMIC DEVELOPMENT

Agricultural development

Tourism

Industries & Skills Development

Mining

SMME support & Trade Development

INFRASTRUCTURE

& SERVICES

Water & Sanitation

Electricity and Lights

Housing and Land

Roads & Stormwater drainage

Waste Management

Free Basic Services